## TEST_CASE_SCENARIO
Projrct Name | Secure Bank
Created By | Fahim Sadman Talukder
Creation Date | 5.11.24
Test Scenario ID | Test Scenario Description | Priority | Number Of Test cases
TS_001 | validate the registered functionality | P0
TS_002 | validate the login functionality | P0
TS_003 | validate the logout functionality | P1
TS_004 | validate the forget password functionality | P0
TS_005 | validate the transaction functionality | P1
TS_006 | validate the functionality of search actions | P5

## TEST_CASE
|  | Product Name | Secure Bank
|  | TC start Date | 1.11.24
|  | TC End Date | 6.11.24
|  | Test Case Developed by | Fahim Sadman Talukder
#SL | Module | Type of Testing | Features | SL_N0 | Test Cases | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bugs Screen Shot | Dev Comments | Final Status | Remarks
Account
|  |  | Sign up | 1 | verifying with valid mail address | user should be able to sign up with correct mail | found as per expectation | abc@gmail.com |  |  |  | Passed
|  |  |  | 2 | Verifying by clicking on the submit button for blank input | An error message will be shown | found as per expectation | N/A |  |  |  | Passed
|  |  |  | 3 | verifying with invalid mail address | user should be unable to sign up with incorrect mail | found as per expectation | xyz |  |  |  | Passed
|  |  |  | 4 | verifying with alphanumeric password | user should be unable to sign up with correct password | found as per expectation | Abc96# |  |  |  | Passed
|  |  |  | 5 | verifying with different passwords in passwords and confirm passwords | user should be able to sign up if the passwords match otherwise don't | found as per expectation | 123\456 |  |  |  | Passed
|  |  |  | 6 | verifying the checkbox of terms and conditions | user should be click on the check box | found as per expectation | N/A |  |  |  | Passed
|  |  |  | 7 | Verify that the user is not allowed to register an account with the same registered email | user should not be able to sign up | found as per expectation | N/A |  |  |  | Passed
|  |  |  | 8 | checking the register button | user should not be able to sign up | found as per expectation | N/A |  |  |  | Passed
|  |  |  | 9 | checking the confirmation mail | user will receive a email | didn't found as expectation | fahimsadman39@gmail.com |  |  |  | failed
|  |  |  | 10 | Verifying whether the validation is added for the password and confirm whether passwords are the same or not | user will able to registration if the password matched otherwise not | found as per expectation | 123456 |  |  |  | Passed
|  |  |  | 11 | Verifying an eye icon added to the password and confirm the password field. | user will be able to show and hide password | didn't found as expectation | 12345678 |  |  |  | failed
|  |  |  | 12 | Verifying captcha is added to the form or not. | user should be proved as human | didn't found as expectation | N/A |  |  |  | failed
|  |  |  | 13 | Verifying example or dummy data shown as placeholder text in the fields. | user should be able to see example in place holder fields | didn't found as expectation | N/A |  |  |  | failed
|  |  |  | 14 | Verifying that user-added information is not removed from the fields in case of any validation fails. | users given data should be saved incase of any validation fails | didn't found as expectation | N/A |  |  |  | failed
|  |  |  | 15 | Verifying that the user can navigate or access the different controls by pressing the ‘Tab’ key on the keyboard | user should be able to move on the next fields | found as per expectation | N/A |  |  |  | Passed
|  |  |  | 16 | Verify that the user should not be able to access the application, software, or pro features until the until the user verifies its email by clicking on the link sent in the email. | user will receive a link via email | didn't found as expectation | N/A |  |  |  | failed
|  |  |  | 17 | Verifying all spelling mistakes on the Register page. | An error message will be shown | found as per expectation | N/A |  |  |  | Passed
|  |  |  | 18 | Verifying password added by the user should be protected, encrypted, and shown in an asterisk(***). | password should be hidden by *** | didn't found as expectation | 12345678 |  |  |  | Passed
|  |  |  | 19 | checking registered as new user link working properly or not | by clicking registered as a new user ,user will be able to sign up | found as per expectation | N/A |  |  |  | Passed
|  |  |  | 20 | checking forget password link working properly not not | by clicking forgot password ,user will be able to reset password | didn't found as expectation | N/A |  |  |  | failed
|  |  | Login | 21 | Verifying the login screen will appear after clicking on a login link or login button | User won't be able to log in | found as expectation | N/A |  |  |  | Passed
|  |  |  | 22 | Verifying all login-related elements and fields are present on the login page | all related fields should be present as client requiremnet | found as expectation | N/A |  |  |  | Passed
|  |  |  | 23 | Verifying login page title | The title should be as client requirement | found as expectation | N/A |  |  |  | Passed
|  |  |  | 24 | Verifying the cursour in the "Email box " by default. | the cursor should remain in the username text box by defaul | found as expectation | N/A |  |  |  | Passed
|  |  |  | 25 | Verifying that there is a checkbox with the label "remember password" on the login page. | There should be a check box for this action. | didn't found as expectation | N/A |  |  |  | failed
|  |  |  | 26 | Verifying that the user will be able to log in with their account with the correct credential | User should be able to login with correct credintial | found as expectation | N/A |  |  |  | Passed
|  |  |  | 27 | Verifying that the password entered should be in encrypted form. | there should be a eye icon for this action. | found as expectation | N/A |  |  |  | Passed
|  |  |  | 28 | Verifying the error message should display after entering an invalid email format. | An error message should display | found as expectation | N/A |  |  |  | Passed
|  |  |  | 29 | Verifying the error message should display after just entering an email address and leaving the password field blank. | An error message should display | found as expectation | N/A |  |  |  | Passed
|  |  |  | 30 | Verifying the displayed error message grammar should be correct. | Error message should be grammartically correct | found as expectation | N/A |  |  |  | Passed
|  |  |  | 31 | Checking logged in user should not log out on closing the browser | User should be log in in case of browser is closed | found as expectation | N/A |  |  |  | Passed
|  |  |  | 32 | Verifying by Keeping mandatory fields blank | Should be blanked to put data. | found as expectation | N/A |  |  |  | Passed
|  |  |  | 33 | verifying the terms and conditions link wheather it is working properly or not | by clicking terms and conditions it will move to another page | found as expectation | N/A |  |  |  | Passed
|  |  | Log Out | 34 | Verifying that a user can successfully log out from the application. | user will be able to log out successfully from the app | found as expectation | N/A |  |  |  | Passed
|  |  |  | 35 | Verifying that the logout button is visible to the logged-in user. | Log out button should be visible to the user | found as expectation | N/A |  |  |  | Passed
|  |  |  | 36 | Verifying that the user is redirected to the login page after logout. | after logging out user will redirected to the login page | found as expectation | N/A |  |  |  | Passed
|  |  |  | 37 | Verifying that logout does not happen during critical actions | at transactions page,user should to be able to log out | didn't found as expectations | N/A |  |  |  | failed
|  |  |  | 38 | Verifying that the user is automatically logged out after a session timeout. | user will be logged out after a inactivity of certain period | didn't found as expectations | N/A |  |  |  | failed
|  |  | Forgot Password | 39 | Verifying by entering registered mail in the field | registered user will receive an link via his/her emal | didn't found as expectation | fahimsadman39@gmail.com |  |  |  | failed
|  |  |  | 40 | Verifying by entering unregistered mail in the field | unregistered user won't receive an link via his/her emal | found as expectation | fahimsadman40@gmail.com |  |  |  | Passed
|  |  |  | 41 | checking the submit button working properly or not | a message will be shown that a link has sent to user | found as expectation | fahimsadman39@gmail.com |  |  |  | Passed
|  |  |  | 42 | verifying user should be login by entering new password | registered user will receive an link via his/her emal | didn't found as expectation | fahimsadman39@gmail.com |  |  |  | failed
|  |  |  | 43 | Verifying that forget password link should be present on the login screen | A link named "forget password "should be present in login page | found as expectation |  |  |  |  | Passed
|  |  |  | 44 | Verifying that on clicking on the forget password link forget password page should open | link should be open in a new page | found as expectation | N/A |  |  |  | Passed
|  |  |  | 45 | Verifying that the email field is present on the forget password page to recover the password. | Email field should be present in"forget password" field | found as expectation | N/A |  |  |  | Passed
|  |  |  | 46 | Verifying the heading displayed in forget password screen should be ” Forget Password “ | display heading named must be "forget password" | found as expectation | N/A |  |  |  | Passed
|  |  |  | 47 | Verifying user should be login successfully with the new password not by the old password. | user should be login successfully with the new password not by the old password | didn't found as expectation | N/A |  |  |  | failed
|  |  | Transactions | 48 | verifying create new button working properly or not | user will be able to create a new transaions | found as expectations | N/A |  |  |  | Passed
|  |  |  | 49 | Checking by invalid receiver email | sender will unable to send money and an error message will be shown | found as expectations | N/A |  |  |  | Passed
|  |  |  | 50 | checking by unregistered receiver email | sender will unable to send money and an error message will be shown | didn't found as expectation | N/A |  |  |  | failed
|  |  |  | 51 | verifying calender is working properly or not | Only Today's date will available to select | found as expectations | N/A |  |  |  | Passed
|  |  |  | 52 | chekcking by putting any alpha numerical value or number in reason fields | Reason can not be a special character or a alpha numerical value or number | didn't found as expectation | N/A |  |  |  | failed
|  |  |  | 53 | verifying by putting calender field empty | Date must be needed for any transactions | found as expectations | N/A |  |  |  | Passed
|  |  |  | 54 | verifying by putting reason field empty | sender will nable to send money | found as expectations | N/A |  |  |  | Passed
|  |  |  | 55 | verifying by putting receiver field empty | sender will unnable to send money and an error message will be shown | found as expectations | N/A |  |  |  | Passed
|  |  |  | 56 | verifyng by putting reference field empty | sender will able to send money | found as expectations | N/A |  |  |  | Passed
|  |  |  | 57 | verifying by putting amount field empty | sender will unable to send money and an error message will be shown | found as expectations | N/A |  |  |  | Passed
|  |  |  | 58 | verifying by sending larger amount of money than the sender have | sender will unnable to send money and an error message will be shown | found as expectations | N/A |  |  |  | Passed
|  |  |  | 59 | checking create button working properly or not | a new transaction history will be created | found as expectations | N/A |  |  |  | Passed
|  |  |  | 60 | checking back to list button working properly or not | user will able to back previous page | found as expectations | N/A |  |  |  | Passed
|  |  |  | 61 | checking details button working properly or not | Transactions history will be shown | found as expectations | N/A |  |  |  | Passed
|  |  |  | 62 | checking by reference and reason field empty | user will be able to create a new transaions | found as expectations | N/A |  |  |  | Passed
|  |  |  | 63 | checking by reference and reason field empty | transactions history will be recorded | didn't found as expectation | N/A |  |  |  | failed
|  |  |  | 64 | checking by giving 00 value in amount fields | user will not be able to create a new transactions | didn't found as expectation | N/A |  |  |  | failed
|  |  |  | 65 | Verifying logout buttoun working properly or not | by clicking logout button user will be logged out | found as expectations | N/A |  |  |  | Passed
|  |  |  | 66 | verifying by searching sender email | same sender email will be shown as a search results | didn't found as expectation | abc@gmail.com |  |  |  | failed
|  |  |  | 67 | verifying by searching receiver email | same receiver email will be shown as a search results | didn't found as expectation | xyz@gmail.com |  |  |  | failed
|  |  |  | 68 | verifying by searching transactions date | same transactions date will be shown as a search results | didn't found as expectation | 2024-11-04 |  |  |  | failed
|  |  |  | 69 | verifying by searching amout | same amount will be shown as a search results | didn't found as expectation | 2 |  |  |  | failed
|  |  |  | 70 | verifying by searching Reason | Same reason for transactions will be shown as reasults | didn't found as expectation | nothing |  |  |  | failed
|  |  |  | 71 | cheking drop down box working properly or not | by clickining 10/25/50/100 ,same number of rows will be displayed | found as expectations | 10 |  |  |  | Passed
|  |  |  | 72 | verifying the choose file for uploading pic (jpg,jepg,png) format | user will be able to upload required format pics | didn't found as expectation | N/A |  |  |  | failed

## Test_case_Report
Test Case Report
Project Name | Secure Bank
Module Name | Account.
Feature Name | sign up & Login &Forget Password & Logout & Transactions
Written By | Fahim Sadman Talukder
Executed By | Fahim Sadman Talukder
Reviewed By
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 49 | 23 | 0 | 0 | 72
Grand Total | 49 | 23 | 0 | 0 | 72

## Test_Metrics
Test Metrics
#SL | Metrics | Description | Result (%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (50/50)*100 = 100
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (0/50)*100 = 0
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (49/72)*100 = 90%
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (23/72)*100 = 10%
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/50)*100 = 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A

## Sheet1
Bug Reporting
# SL 01
Issue: Registered with invalid email address.
Reproducing Steps:
1. Goto the URL http://localhost:1337/ 2. Click on the Sign up button. 3. Fill all the files with valid credentials. 4. Click 'REGISTER'.
Env: Production.
Module: Register
Priority: High ¦ Medium ¦ Low
Severity: Blocker ¦ Critical ¦ Major ¦ Minor
Expected: user should receive a confirmation mail
Responsible QA: FAHIM SADMAN TALUKDER
Bug Reporting
# SL 02
Issue: An eye icon is not added at the password field
Reproducing Steps:
1. Goto the URL http://localhost:1337/ 2. Click on the Login button . 3. Fill all the fileds with valid credentials.
Env: Production.
Module: Register
Priority: High ¦ Medium ¦ Low
Severity: Blocker ¦ Critical ¦ Major ¦ Minor
Screenshoot:An eye icon is not added at the password field
Expected: An eye Icon should be added to show the password
Responsible QA: FAHIM SADMAN TALUKDER
Bug Reporting
# SL 03
Issue: Forget password option does not working.
Reproducing Steps:
1. Goto the URL http://localhost:1337/ 2. Click on the forget password button. 3. Fill all the files with valid credentials. 4. Click 'submit'.
Env: Production.
Module: Forget password
Priority: High ¦ Medium ¦ Low
Severity: Blocker ¦ Critical ¦ Major ¦ Minor
Expected: user should receive a confirmation mail
Responsible QA: FAHIM SADMAN TALUKDER
Bug Reporting
# SL 04
Issue: unregistered user can make transactions.
Reproducing Steps:
1. Goto the URL http://localhost:1337/ 2. Click on the login password button. 3. Fill all the files with valid credentials. 4. Click 'submit'.
4. Goto the transactions page 5. Fill all the files with valid credentials. 4. Click 'create'.
Module: Transactions
Priority: High ¦ Medium ¦ Low
Severity: Blocker ¦ Critical ¦ Major ¦ Minor
Expected: Unregistered user should not be able to make any transactions
Responsible QA: FAHIM SADMAN TALUKDER